## README
Insurance AI Platform — Phase 1 JIRA Export
Epic / Story / Task / Subtask breakdown, generated from the real project artifacts
Source of truth | Every row in this workbook traces to a real artifact in github.com/btholath/insurance-ai-platform: spec.md (User Stories, FR-XXX requirements), tasks.md (all 74 tasks, including T053a/T053b added via /speckit-analyze remediation), and the /speckit-analyze coverage report (FR-to-task traceability).
Hierarchy used | Epic (1) → Story/Task (8, parent-level) → Subtask (74). This mirrors standard JIRA structure: 'Story' = user-facing capability (from spec.md's 5 User Stories), 'Task' = technical work with no natural user-facing framing (Setup, Foundational, Polish phases).
Status as of | 2026-08-01. T001-T030 (Setup + Foundational) are Done, independently verified against the live database and source code — see readme-runbook-phase1.md in the repo for the full verification trail. T031-T072 (+T053a/T053b) are To Do.
How to import into real JIRA | The 'Subtasks' sheet's columns (Issue Type, Summary, Parent, Description, Status, Labels) match JIRA's CSV importer field names closely enough to use directly — export that sheet as CSV, map 'Parent' to Epic Link or Parent depending on your project type (company-managed vs. team-managed), then re-run the import for the 'Stories & Tasks' sheet first so parent keys exist before subtasks reference them.
Assumption disclosed | JIRA issue keys (INSAI-1, INSAI-2, ...) are placeholder keys for this export — they are not real keys from a live JIRA instance, since this project has not actually been entered into JIRA. Renumber to match your real project key on import.
Assumption disclosed | FR-032/033/034's task mapping on the 'Traceability Matrix' sheet is marked where it was directly confirmed against a task's own cited FR number in tasks.md's text, versus where it is an inference based on requirement-text similarity — see that sheet's 'Confidence' column.

## Dashboard
Phase 1 Progress Dashboard
All figures below are live formulas referencing the Subtasks sheet — they recalculate if task statuses change.
Metric | Value | Notes
Total subtasks | 74 | All T-numbers, including T053a/T053b
Done | 30 | T001-T030 — Setup + Foundational
To Do | 44 | T031-T072, +T053a/T053b
% Complete | 40.54% | Done ÷ Total
Parallel-capable tasks [P] | 41 | Can run concurrently per tasks.md
Breakdown by parent Story/Task
Parent Key | Parent Summary | Subtask Count | Done | To Do | % Complete
INSAI-2 | Setup: Repository Scaffolding | 6 | 6 | 0 | 100%
INSAI-3 | Foundational: Django Project, RBAC, Audit, Compose | 24 | 24 | 0 | 100%
INSAI-4 | US1: Platform Runs Locally | 5 | 0 | 5 | 0%
INSAI-5 | US2: Roles & RBAC Enforced | 12 | 0 | 12 | 0%
INSAI-6 | US3: Unalterable Audit Record | 12 | 0 | 12 | 0%
INSAI-7 | US4: System Health at a Glance | 7 | 0 | 7 | 0%
INSAI-8 | US5: Automated Tests From Day One | 4 | 0 | 4 | 0%
INSAI-9 | Polish & Cross-Cutting Validation | 4 | 0 | 4 | 0%

## Epic
Issue Type | Key | Summary | Description | Priority | Status | Reporter | Labels | Epic Name
Epic | INSAI-1 | Phase 1 - Foundation: Platform Skeleton & Role-Based Access | This feature establishes the foundation on which every later module (Customer, Policy, Claims, Risk, Fraud, Behavior, Prompt Library, LLM Services, CRM, Dashboards, Reporting, Administration) will be built. It delivers no business-facing insurance functionality of its own. Its value is that it makes the next phases possible, and it makes the platform's two non-negotiable guarantees - server-side role enforcement and audit logging - structurally available from day one rather than retrofitted later. Scope: an identity and access foundation, a running local service environment, an operational health signal, an append-only audit record, and a working automated-test capability. (Source: spec.md Overview, specs/001-foundation-platform-skeleton/spec.md) | P1 - Highest | In Progress | btholath | phase-1, foundation, rbac, audit-logging | Foundation

## Stories & Tasks
Issue Type | Key | Epic Link | Summary | Description | Acceptance Criteria (from spec.md) | Priority | Status | Story Points (est.) | Subtask Range
Task | INSAI-2 | INSAI-1 | Setup: Repository Scaffolding & Dependency Management | Repository scaffolding, dependency manifest, and Docker image definition. Nothing here is Django-app code yet. (tasks.md Phase 1: Setup) | Repo has structure, dependency manifest, and container build definition before any application code is written. | P2 - High | Done | 3 | T001-T006
Task | INSAI-3 | INSAI-1 | Foundational: Django Project, User Model, RBAC, Audit, Compose | Django project configuration, the custom User model (which must be in place before the first migration and cannot be swapped later), the single RBAC mechanism, the append-only audit log, Docker Compose orchestration, and the pytest/Factory Boy harness. Every user story depends on this phase. (tasks.md Phase 2: Foundational) | Django project boots under Docker Compose; the custom User model and RBAC mechanism exist; the audit log is append-only at both ORM and DB layers; health check probes work; the test harness is wired. | P1 - Highest | Done | 13 | T007-T030
Story | INSAI-4 | INSAI-1 | US1: Platform Operator Runs the Whole System Locally | A developer or System Administrator clones the repository onto a clean machine and brings the entire platform up locally with a single documented command sequence. The application, its database, and its cache all start and become reachable, with no external cloud service required. (spec.md User Story 1, Priority P1) | Given a clean checkout, When the operator follows the documented startup sequence, Then app/db/cache all reach a running state without manual intervention beyond copying the example environment file. Data survives a restart. No service requires outbound network access. | P1 - Highest | To Do | 3 | T031-T035
Story | INSAI-5 | INSAI-1 | US2: Administrator Assigns Roles and the System Enforces Them | A System Administrator creates user accounts and assigns each one exactly one of the nine organizational roles. Every restricted action is decided server-side, and refused if the role does not permit it - regardless of what the UI shows or how the request was constructed. (spec.md User Story 2, Priority P1) | Given a System Administrator, When they create/patch an account's role, Then it's recorded and enforced immediately. Given any other role or an unauthenticated caller, When they attempt a restricted action, Then it is refused (403 collection / 404 detail, non-disclosing). | P1 - Highest | To Do | 8 | T036-T047
Story | INSAI-6 | INSAI-1 | US3: Compliance Officer Sees an Unalterable Record | Every user-account creation and role change writes an append-only audit record with actor, action, target, timestamp, outcome, and before/after state. No part of the platform can modify or delete an existing record. (spec.md User Story 3, Priority P2) | Given an admin action, When it's saved, Then an audit record is created with full required fields. Given an existing record, When modification/deletion is attempted (ORM or raw SQL), Then it is refused. A Compliance Officer can retrieve history chronologically. | P2 - Medium | To Do | 8 | T048-T057 (+T053a, T053b)
Story | INSAI-7 | INSAI-1 | US4: Operator Confirms System Health at a Glance | An unauthenticated GET /health/ reports healthy/unhealthy status for Postgres and Redis within 5 seconds, identifying any failing dependency individually, without disclosing sensitive details. (spec.md User Story 4, Priority P2) | Given all services up, When /health/ is queried without credentials, Then it reports healthy. Given the DB is down, When queried, Then it reports unhealthy and names the database specifically, within 5s. | P2 - Medium | To Do | 5 | T058-T064
Story | INSAI-8 | INSAI-1 | US5: Developer Writes and Runs Automated Tests From Day One | A developer runs the full automated test suite with a single command, and can construct realistic test data - including users in any of the nine roles - without hand-writing setup boilerplate. (spec.md User Story 5, Priority P2) | Given a fresh checkout, When the test command runs, Then the suite executes, reports pass/fail, produces coverage, and leaves dev data untouched. A test user in any role is a single factory call. | P2 - Medium | To Do | 3 | T065-T068
Task | INSAI-9 | INSAI-1 | Polish & Cross-Cutting Validation | Final validation against the complete quickstart guide and constitution re-check; no new functional surface. (tasks.md Phase 8: Polish) | Full quickstart.md re-run (all 5 scenarios) passes end-to-end. README/setup docs get a fresh-reader timing check against SC-001 (under 30 minutes). Final coverage report reviewed. | P3 - Low | To Do | 3 | T069-T072

## Subtasks
Issue Type | Key | Parent | Summary | Status | Test/Impl | Parallel [P] | FR Reference(s)
Subtask | T001 | INSAI-2 | Create root directories per plan.md's Project Structure (config/, apps/, docker/django/, scripts/, tests/integration/) | Done | Implementation | No
Subtask | T002 | INSAI-2 | Create pyproject.toml: Django/DRF/psycopg/redis/django-environ/gunicorn deps + pytest/factory-boy dev deps, pytest & coverage config | Done | Implementation | No | FR-031
Subtask | T003 | INSAI-2 | Create docker/django/Dockerfile (python:3.13-slim-bookworm, entrypoint scripts/entrypoint.sh) | Done | Implementation | Yes
Subtask | T004 | INSAI-2 | Create scripts/entrypoint.sh: wait for Postgres, run migrate, exec gunicorn | Done | Implementation | Yes
Subtask | T005 | INSAI-2 | Create .env.example listing every required setting (SECRET_KEY, DEBUG, POSTGRES_*, REDIS_URL, ALLOWED_HOSTS) | Done | Implementation | Yes | FR-004
Subtask | T006 | INSAI-2 | Create .gitignore (.env, __pycache__, .pytest_cache, htmlcov, .coverage, venv) | Done | Implementation | Yes
Subtask | T007 | INSAI-3 | manage.py at repo root, pointing to config.settings.dev | Done | Implementation | No
Subtask | T008 | INSAI-3 | config/__init__.py, config/wsgi.py, config/asgi.py | Done | Implementation | No
Subtask | T009 | INSAI-3 | config/settings/base.py: INSTALLED_APPS, AUTH_USER_MODEL, django-environ, fail-fast REQUIRED_SETTINGS check | Done | Implementation | No | FR-004, FR-005
Subtask | T010 | INSAI-3 | config/settings/dev.py: imports base, local-dev overrides | Done | Implementation | Yes
Subtask | T011 | INSAI-3 | config/settings/test.py: imports base, MD5PasswordHasher for test speed | Done | Implementation | Yes
Subtask | T012 | INSAI-3 | config/urls.py: root URLconf mounting /health/ and each app's /api/ routes | Done | Implementation | No
Subtask | T013 | INSAI-3 | apps/core: AppConfig + TimeStampedModel abstract base | Done | Implementation | No
Subtask | T014 | INSAI-3 | apps/core/permissions.py: HasRole(*roles) DRF permission factory - no superuser bypass, deny-by-default, 404-not-403 on detail routes | Done | Implementation | No | FR-011, FR-012, FR-014, FR-015
Subtask | T015 | INSAI-3 | apps/accounts: __init__.py, apps.py | Done | Implementation | Yes
Subtask | T016 | INSAI-3 | apps/accounts/models.py: Role(TextChoices) with 9 values, User(AbstractBaseUser, PermissionsMixin), user_role_valid CheckConstraint | Done | Implementation | No | FR-009, FR-010
Subtask | T017 | INSAI-3 | apps/accounts/managers.py: UserManager.create_user/create_superuser, requires role, normalizes email | Done | Implementation | No | FR-008
Subtask | T018 | INSAI-3 | Generate & commit FIRST migration for apps/accounts - must precede every other app's migration (AUTH_USER_MODEL) | Done | Implementation | No
Subtask | T019 | INSAI-3 | apps/accounts/admin.py: register User in Django admin, exclude raw password display | Done | Implementation | Yes
Subtask | T020 | INSAI-3 | apps/accounts/factories.py: UserFactory with per-role trait, single-call role creation | Done | Implementation | Yes | FR-030
Subtask | T021 | INSAI-3 | apps/audit: __init__.py, apps.py | Done | Implementation | Yes
Subtask | T022 | INSAI-3 | apps/audit/models.py: AuditLog model, save()/delete() override to raise, custom queryset overriding update()/delete() | Done | Implementation | No | FR-018, FR-019, FR-023
Subtask | T023 | INSAI-3 | Generate apps/audit migration incl. RunSQL: PostgreSQL BEFORE UPDATE OR DELETE trigger audit_log_immutable | Done | Implementation | No | FR-019
Subtask | T024 | INSAI-3 | apps/audit/services.py: record_action() - writes one AuditLog row inside caller's transaction.atomic() | Done | Implementation | Yes | FR-022
Subtask | T025 | INSAI-3 | apps/audit/factories.py: AuditLogFactory for direct test construction | Done | Implementation | Yes
Subtask | T026 | INSAI-3 | apps/health: __init__.py, apps.py | Done | Implementation | Yes
Subtask | T027 | INSAI-3 | apps/health/checks.py: check_database()/check_cache() with 2s bounded timeouts, never raising | Done | Implementation | No | FR-027
Subtask | T028 | INSAI-3 | tests/conftest.py: shared fixtures - api_client, user_in_role, authenticated_client | Done | Implementation | Yes
Subtask | T029 | INSAI-3 | Configure docker-compose.yml: web/db/redis services, healthchecks, named volumes, ports not published by default | Done | Implementation | No
Subtask | T030 | INSAI-3 | Verify foundational stack boots: docker compose up --build -d, confirm healthy, migrate applies cleanly | Done | Implementation | No | FR-001
Subtask | T031 | INSAI-4 | Integration test: real DB + Redis connections succeed via configured settings | To Do | Test | Yes
Subtask | T032 | INSAI-4 | Test: missing required env var raises ImproperlyConfigured naming the missing setting | To Do | Test | Yes | FR-005
Subtask | T033 | INSAI-4 | README.md: exact setup sequence (clone, cp .env.example .env, up --build -d, createsuperuser, verify /health/) | To Do | Implementation | No | FR-007
Subtask | T034 | INSAI-4 | Add commented-out host port mapping for db in docker-compose.yml (local psql access) | To Do | Implementation | No
Subtask | T035 | INSAI-4 | Manually verify SC-010 (restart persistence) and SC-011 (no external network dependency) | To Do | Implementation | No | SC-010, SC-011
Subtask | T036 | INSAI-5 | Test: User rejects role outside 9 values at full_clean() and DB CheckConstraint level | To Do | Test | Yes | FR-010
Subtask | T037 | INSAI-5 | Test: HasRole matrix - unauthenticated/wrong-role/correct-role/null-role/superuser-not-bypassed | To Do | Test | Yes | FR-014
Subtask | T038 | INSAI-5 | Contract test: full 9-role x unauthenticated RBAC matrix against POST/GET /api/users/ | To Do | Test | Yes | FR-033, SC-002, SC-003
Subtask | T039 | INSAI-5 | Test: invalid role value on POST /api/users/ returns 400, no account created | To Do | Test | Yes | FR-010
Subtask | T040 | INSAI-5 | Test: PATCH role change takes effect on affected user's next request, no restart needed | To Do | Test | Yes | FR-016
Subtask | T041 | INSAI-5 | Test: UserFactory produces a valid user for each of 9 roles in a single call | To Do | Test | Yes | FR-030, SC-009
Subtask | T042 | INSAI-5 | apps/accounts/serializers.py: UserSerializer, password never in response | To Do | Implementation | Yes
Subtask | T043 | INSAI-5 | apps/accounts/views.py: UserViewSet, HasRole(SYSTEM_ADMINISTRATOR), writes audit records via record_action() | To Do | Implementation | No | FR-017, FR-020
Subtask | T044 | INSAI-5 | apps/accounts/urls.py: route /api/users/ and /api/users/{id}/ | To Do | Implementation | No
Subtask | T045 | INSAI-5 | Session auth endpoints: POST /api/auth/login/, /api/auth/logout/, generic failure message | To Do | Implementation | No
Subtask | T046 | INSAI-5 | customers/policies/claims placeholder apps: one HasRole-restricted GET .../placeholder/ view each | To Do | Implementation | No | FR-006
Subtask | T047 | INSAI-5 | Test: each placeholder endpoint permits documented roles, refuses all others + unauthenticated | To Do | Test | Yes | FR-033
Subtask | T048 | INSAI-6 | Test: AuditLog.save()/.delete()/queryset .update()/.delete() all raise on an existing record (ORM layer) | To Do | Test | Yes | FR-019, SC-005
Subtask | T049 | INSAI-6 | Integration test: raw DB cursor UPDATE/DELETE against audit_auditlog rejected by the trigger (DB layer) | To Do | Test | Yes | FR-019, SC-005
Subtask | T050 | INSAI-6 | Test: record_action() writes inside caller's transaction; simulated audit-insert failure rolls back the enclosing action too | To Do | Test | Yes | FR-022
Subtask | T051 | INSAI-6 | Test: creating a user then changing their role produces exactly user.created then user.role_changed audit entries | To Do | Test | Yes | FR-020, SC-004
Subtask | T052 | INSAI-6 | Test: deleting a User with audit entries leaves them readable, actor null, actor_identifier/actor_role intact | To Do | Test | Yes | FR-021
Subtask | T053 | INSAI-6 | Contract test: GET /api/audit/ and .../history/ - RBAC (Compliance Officer + Sys Admin only), chronological order | To Do | Test | Yes | FR-024
Subtask | T053a | INSAI-6 | [Added via /speckit-analyze F1 fix] Test: history for a target with ZERO entries returns 200 + count:0, not 404 | To Do | Test | Yes | FR-024
Subtask | T053b | INSAI-6 | [Added via /speckit-analyze F2 fix] Test: after actor deletion, API still serializes actor:null + actor_identifier/actor_role (API layer, complements T052) | To Do | Test | Yes | FR-021
Subtask | T054 | INSAI-6 | Test: POST/PUT/PATCH/DELETE on any audit route return 405 Method Not Allowed | To Do | Test | Yes
Subtask | T055 | INSAI-6 | apps/audit/serializers.py: read-only AuditLogSerializer | To Do | Implementation | Yes
Subtask | T056 | INSAI-6 | apps/audit/views.py: AuditListView + AuditHistoryView, HasRole(COMPLIANCE_OFFICER, SYSTEM_ADMINISTRATOR), read-only | To Do | Implementation | No | FR-024
Subtask | T057 | INSAI-6 | apps/audit/urls.py: route /api/audit/ and /api/audit/history/<type>/<id>/ | To Do | Implementation | No
Subtask | T058 | INSAI-7 | Test: check_database()/check_cache() return ok/error (never raising), within 2s timeout | To Do | Test | Yes
Subtask | T059 | INSAI-7 | Contract test: GET /health/ returns 200 when healthy, 503 identifying the correct failing dependency | To Do | Test | Yes | FR-026, FR-027, SC-007
Subtask | T060 | INSAI-7 | Test: /health/ response contains ONLY status + checks.*.status - no host/port/credential/version leakage | To Do | Test | Yes | FR-028
Subtask | T061 | INSAI-7 | Test: /health/ returns within bounded time even when a dependency would otherwise hang | To Do | Test | Yes | FR-027, SC-006
Subtask | T062 | INSAI-7 | apps/health/views.py: unauthenticated APIView calling both checks, 200/503 per contracts/health.md | To Do | Implementation | No | FR-025
Subtask | T063 | INSAI-7 | apps/health/urls.py: route GET /health/ at root path (not under /api/) | To Do | Implementation | No
Subtask | T064 | INSAI-7 | Add web service healthcheck to docker-compose.yml (interval 10s, timeout 5s, retries 5, start_period 30s) | To Do | Implementation | No
Subtask | T065 | INSAI-8 | Test: pytest-django's test database is distinct from the configured dev database (isolation) | To Do | Test | Yes | FR-032
Subtask | T066 | INSAI-8 | Document --reuse-db default + --create-db variant in README/quickstart cross-reference | To Do | Implementation | No
Subtask | T067 | INSAI-8 | Run full suite via docker compose exec web pytest --cov-report=term-missing; confirm pass, coverage, <2min runtime | To Do | Implementation | No | SC-008
Subtask | T068 | INSAI-8 | Confirm pytest run twice in a row produces identical dev-database row counts | To Do | Implementation | No | FR-032
Subtask | T069 | INSAI-9 | Run quickstart.md Scenario 1 end-to-end: full environment, outbound-blocked check, restart-persistence check | To Do | Implementation | Yes | SC-010, SC-011
Subtask | T070 | INSAI-9 | Run quickstart.md Scenarios 2-5 end-to-end: RBAC matrix, audit immutability (both layers), health degradation, full test suite | To Do | Implementation | Yes
Subtask | T071 | INSAI-9 | Review README/setup docs against FR-007/SC-001: fresh-reader dry run, time to running+tested system (<30 min) | To Do | Implementation | No | FR-007, SC-001
Subtask | T072 | INSAI-9 | Final coverage report review: apps/core, accounts, audit, health all have meaningful coverage | To Do | Implementation | No | FR-031

## Traceability Matrix
Requirement Traceability Matrix
Source: /speckit-analyze coverage report (FR-001 to FR-031, Confidence=Confirmed) and direct tasks.md text citations (FR-032 to FR-034, Confidence=Confirmed where a task explicitly cites the FR number).
FR ID | Requirement (from spec.md) | Story | Task ID(s) | Confidence
FR-001 | Single declarative local orchestration (all services) | INSAI-3 | T029, T030 | Confirmed (analyze report)
FR-002 | No required call to external cloud service | INSAI-4 | T035 | Confirmed (analyze report)
FR-003 | Stored data survives stop/restart | INSAI-4 | T035 | Confirmed (analyze report)
FR-004 | External config via env, example file provided | INSAI-3 | T005, T009 | Confirmed (analyze report)
FR-005 | Fail-fast on missing required config | INSAI-3/4 | T009, T032 | Confirmed (analyze report)
FR-006 | customers/policies/claims module layout matches BRD | INSAI-5 | T046 | Confirmed (analyze report)
FR-007 | Setup/startup/test steps fully documented | INSAI-4 | T033 | Confirmed (analyze report)
FR-008 | Authenticatable user accounts | INSAI-3/5 | T016, T017, T045 | Confirmed (analyze report)
FR-009 | Exactly one of 9 roles per account | INSAI-3 | T016 | Confirmed (analyze report)
FR-010 | Reject any role outside the 9 defined values | INSAI-3/5 | T016, T036, T039 | Confirmed (analyze report)
FR-011 | Every access decision evaluated server-side | INSAI-3 | T014 | Confirmed (analyze report)
FR-012 | 404 (not 403) non-disclosure on detail routes | INSAI-3/5 | T014, T038 | Confirmed (analyze report)
FR-013 | Refuse unpermitted action, target data unchanged | INSAI-5 | T038, T040 | Confirmed (analyze report)
FR-014 | Deny-by-default for null/invalid role | INSAI-5 | T037 | Confirmed (analyze report)
FR-015 | Single reusable RBAC mechanism | INSAI-3 | T014 | Confirmed (analyze report)
FR-016 | Role change takes effect immediately, no restart | INSAI-5 | T040 | Confirmed (analyze report)
FR-017 | Only System Administrator manages users/roles | INSAI-5 | T043 | Confirmed (analyze report)
FR-018 | Audit record captures actor/action/target/time/outcome/before/after | INSAI-3 | T022 | Confirmed (analyze report)
FR-019 | Audit records are append-only (ORM + DB layers) | INSAI-3/6 | T022, T023, T048, T049 | Confirmed (analyze report)
FR-020 | Audit write on user creation and role change | INSAI-5/6 | T043, T051 | Confirmed (analyze report)
FR-021 | Audit entry survives actor deletion, identifiable | INSAI-6 | T052, T053b | Confirmed (analyze report)
FR-022 | Atomic audit write (same transaction as the action) | INSAI-3/6 | T024, T050 | Confirmed (analyze report)
FR-023 | Generic/reusable audit schema for future modules | INSAI-3 | T022 | Confirmed (analyze report)
FR-024 | Audit history retrievable in chronological order | INSAI-6 | T053, T053a, T056 | Confirmed (analyze report)
FR-025 | Health endpoint reachable without authentication | INSAI-7 | T062 | Confirmed (analyze report)
FR-026 | Health reports per-dependency status individually | INSAI-7 | T059 | Confirmed (analyze report)
FR-027 | Health returns within bounded time, machine-detectable | INSAI-3/7 | T027, T059, T061 | Confirmed (analyze report)
FR-028 | Health discloses no sensitive configuration detail | INSAI-7 | T060 | Confirmed (analyze report)
FR-029 | Automated test suite runnable via single command | INSAI-8 | T067 | Confirmed (analyze report)
FR-030 | Single-call test-data builder for any of the 9 roles | INSAI-3/5 | T020, T041 | Confirmed (analyze report)
FR-031 | Test suite produces a coverage measurement | INSAI-2/8/9 | T002, T067, T072 | Confirmed (analyze report)
FR-032 | Tests run against isolated data, dev data untouched | INSAI-8 | T065, T068 | Confirmed (task cites FR)
FR-033 | Tests prove refusal/permission per role, incl. placeholders | INSAI-5 | T038, T047 | Confirmed (task cites FR)
FR-034 | Tests prove audit write + immutability on account/role changes | INSAI-6 | T048, T049, T051 (inferred from requirement-text overlap - not explicitly FR-034-tagged in any task's own citation; verify against a live tasks.md before relying on this row) | Inferred - verify